**FY 2023 Scenario Updates**

|  |  |  |  |
| --- | --- | --- | --- |
| **Scenario** | **Date originally published** | **Tentative release date of draft version** | **Status Update** |
| Authority Temporarily Precluded from Obligation | 2001 | May 2023 | Have had internal meetings with OMB and have made updates to the background and transactions. Additional meeting with OMB for approval pending. |
| Receipts Not Available for Obligation Upon Collection | 2001 | June 2023 | Have had internal meetings with OMB and have made updates to the background and transactions. A new USSGL is involved in this scenario, which will be presented at April IRC. Pending approval of the USSGL, a draft version is nearing completion. |
| Advance Appropriation | 2002 | July 2023 | Have had internal meetings with OMB to lay the groundwork and transactions have been reviewed. The verbiage in the background section is under review with BAAS, GLAB, and OMB. Potential updates to the background section will coincide with OMB Circular A-11 updates. |
| Appropriation Transfers | 1997 | May 2023 | Have had several meetings with OMB to lay the groundwork and modifications and updates underway. Follow up meeting scheduled for April 20th to review updates. The name of this scenario may be changed to say “Non Expenditure Transfers.” |
| Transfer of Prior Year Balances | 2000 | August IRC | Assigned but work has not yet begun. |
| Congressional Deferral | 2004 | August IRC | Assigned but work has not yet begun. |
| Leases -Intragovernmental | 2002 based on SFFAS 5/6, 2023 based on SFFAS 54 | 4/13/23 | Finalized |
| Leases – Short Term | 2002 based on SFFAS 5/6, 2023 based on SFFAS 54 | 4/13/23 | Finalized |
| Leases – RTU (Budgetary Capital) | 2002 based on SFFAS 5/6, 2023 based on SFFAS 54 | 4/13/23 | Finalized |
| Leases – RTU (Budgetary Operating no cancellation) | 2002 based on SFFAS 5/6, 2023 based on SFFAS 54 | 4/13/23 | Finalized |
| Leases – RTU (Budgetary Operating with cancellation) | 2002 based on SFFAS 5/6, 2023 based on SFFAS 54 | 4/13/23 | Finalized |
| Technology Modernization Fund (Addendum #2) | 2018 | 4/30/23 | GLAB has collaborated with OMB and GSA on Addendum #2 which will address Trust Funds. We are currently working on adding the addendum. |
| Foreign Military Sales | N/A | June 2023 | GLAB has worked extensively with DoD to assist in formulating the FMS Scenario. OMB concurrence has not fully happened yet. |